SE3003 - Software Project Management

M2 — Project Plan Baseline Report

Project title: GymGym-A – Smart Workout Tracker & Analyzer

Team name/number: GymGym-A

Team members and roles: Mehmet Egemen Karagöz (230717063 – Project Manager / Facilitator), Doğukan Direksiz (230717015 – Product Owner Representative), Çağatay Oruk (230717041 – Technical Lead), Berat Kaan Akcan (230717052 – Quality and Test Lead)

Submission date: 01.11.2026

Document version: 1.0 (Approved Baseline)

Repository/project board link: Repo: https://github.com/GymGym-A-Project/GymGym-A-SE3003 | Board: https://github.com/users/se-230717041/projects/1/views/1?layout_template=board

# 1. Executive Summary

This M2 Project Plan Baseline Report defines the agreed baseline plan that will govern the execution of the GymGym-A (Smart Workout Tracker & Analyzer) project from Week 5 to Week 14. Built on the M1 Project Charter, the scope baseline is structured into 8 Epics (work packages) prioritized with the MoSCoW method: 6 Must work packages (Project Setup, Authentication, ~150-Exercise Library, Routine Builder, Active Workout Logger with Ghost Values, and Workout History) and 2 Should work packages (the 30-Day Rule-Based + Gemini AI Plateau Analyzer, and UX Enhancements covering the Calendar View, Google Sign-In and Starter Programs). Using Planning Poker validated by sub-task breakdown, total project effort is estimated at 80 Story Points (~192 ideal person-hours; an average of 6 hours per person per week over 8 active development weeks for our 4-person team). Delivery is split into four 2-week Agile sprints: Sprints 1 and 2 deliver 100% of the Must features before the M3 Midterm Review (Weeks 8–9); Sprint 3 delivers the AI Plateau Analyzer and absorbs the Change Event in Weeks 9–12; and Sprint 4 focuses on quality hardening, regression testing and the M5 Final Presentation.

# 2. Scope Baseline

## 2.1 Work Breakdown Structure

| ID | Epic / Work Package | Description | Priority | Acceptance Criteria / Output |
| --- | --- | --- | --- | --- |
| WP-01 | Epic 1: Core Architecture, CI and Dataset Setup | Set up the Flutter repository architecture, the Firebase project connection and local caching, and bundle the cleaned 152-exercise JSON dataset with its 180×180 GIFs/images into the app. | Must | The app builds on Android/iOS emulators; the Firebase connection is verified; the 152 exercises load locally in under 100 ms with the mandatory "© Gym visual" attribution visible. |
| WP-02 | Epic 2: User Authentication and Session Management | Implement email/password sign-up, login, password reset, persistent session state and logout using Firebase Auth. | Must | Users can sign up and log in, and stay logged in after the app restarts; clear error messages are shown for invalid credentials; user data is isolated per UID. |
| WP-03 | Epic 3: Verified Exercise Library and Filtering | A searchable, filterable catalog of ~150 exercises grouped by primary target muscle group (chest, back, legs, shoulders, arms, core), with 180×180 images/GIFs and descriptions. | Must | Users can filter exercises by muscle group and search by keyword (< 150 ms response); every detail card shows the 180×180 image/GIF and the "© Gym visual" attribution. |
| WP-04 | Epic 4: Custom Routine Builder (CRUD) | Create, view, edit, reorder and delete custom workout templates (e.g. "Push Day", "Leg Day") containing selected exercises and target set counts. | Must | Users can create and edit routines with 1–15 exercises; changes are saved instantly to Firestore and the offline cache. |
| WP-05 | Epic 5: Active Workout Logger and Ghost Values | Start a workout from a routine, log weight (kg) and reps per set, add/remove exercises dynamically during the workout, show the previous session's weight/rep values faintly in the input fields ("ghost values"), and present an end-of-workout summary screen. | Must | For each exercise, the ghost values from the user's last completed session are pre-filled faintly in under 200 ms; when the workout is finished, a timestamped session is saved and a total volume/set summary is shown. |
| WP-06 | Epic 6: Workout History and Per-Exercise Progress | A chronological list of completed workout sessions with full set details, and an exercise history tab showing each exercise's max weight / volume progress over time. | Must | Completed workouts appear immediately in chronological order; selecting any exercise shows its weight and rep performance by date. |
| WP-07 | Epic 7: On-Demand 30-Day Plateau Analyzer and AI Advisor | A rule-based engine scans the last 30 days of logs to detect progress plateaus (no increase in either max weight or total volume for the same exercise over ≥3 sessions). A backend function queries the Gemini API to explain the plateau and suggests 2–3 alternative exercises only from the ~150-exercise library. | Should | The plateau rule correctly flags stalled exercises; the AI explanation and 2–3 library-verified alternatives return in < 5 s; hallucinated IDs are discarded; the rule-based fallback works offline; the "Advisory only" notice is shown. |
| WP-08 | Epic 8: Secondary UX Enhancements (Calendar, Google Sign-In and Starter Programs) | A monthly calendar view highlighting workout days, one-tap Google Sign-In integration, and 3 ready-made static starter routines (Push/Pull/Legs, Upper/Lower, Full Body). | Should | The calendar highlights all workout days in the selected month; new users can copy any of the 3 starter routines into their own list with one tap. |

## 2.2 Scope Boundaries

Post-M1 Scope Alignment and Technical Clarifications:

• The core Must and Should product features are fully consistent with M0 and M1; only one important technical boundary was clarified as a result of our Week 3 dataset spike: the Exercise Library (WP-03) is locked to a statically bundled, pre-verified JSON subset of ~150 exercises (152 records) instead of fetching raw external files at runtime. This decision eliminates broken external image links and guarantees 100% deterministic ID matching for the AI Plateau Analyzer (WP-07).

• Firm Out-of-Scope Boundaries (Won't Have): Diet/calorie tracking, social feeds/leaderboards, AI-generated workout programs from scratch based on body measurements (excluded due to medical-liability and privacy risks), smartwatch integration, dynamic calendar rescheduling, and user video uploads are firmly out of scope.

• Prioritized Cut Order: To protect the M3 Midterm Review and M5 Final Presentation deadlines, if team velocity drops, Should features are removed from scope or deferred in this order: (1) Static Starter Programs, (2) Monthly Calendar View, (3) Google Sign-In, and (4) the Gemini AI natural-language layer (falling back to the deterministic rule-based plateau output).

# 3. Estimation and Assumptions

## 3.1 Estimation Method

Selected Method: Planning Poker validated by Bottom-Up Ideal-Hour Estimation (Fibonacci Story Points: 1, 2, 3, 5, 8, 13).

Rationale and Limitations:

• Why Planning Poker + Bottom-Up: As a 4-person student team with different levels of experience in Flutter and Firebase, a group Planning Poker session surfaces the hidden architectural and testing assumptions of the different roles (Tech Lead, QA, PO, PM) and prevents anchoring bias. Each Work Package (WP-01 – WP-08) was broken down into concrete sub-tasks and estimated in Story Points (1 Story Point ≈ 2.4 ideal person-hours), giving a total baseline of 80 Story Points (192 ideal hours).

• Capacity Calibration: With 4 team members each contributing ~6 productive hours per week over 8 active development weeks (Weeks 5–12), our total capacity is 192 person-hours (an average of 20 Story Points per 2-week sprint). The sprint load is deliberately front-loaded: Sprint 1 = 30 SP (WP-01–WP-04), Sprint 2 = 26 SP (WP-05–WP-06), Sprint 3 = 14 SP (WP-07), Sprint 4 = 6 SP (WP-08); the PM-QA work (4 SP) is spread across the sprints. The 56 SP Must load in Sprints 1–2 exceeds the nominal capacity of 40 SP; this gap will be closed by WP-01 being partly done already through the Week 3 spike and by members working at the upper end of the 6–8 hour range during Sprints 1–2. Sprints 3–4 are planned lighter to leave a buffer for the Change Event and testing.

• Limitations: Story Point estimates made at the start of the semester carry ±25% uncertainty, especially for third-party API latency (WP-07) and complex UI state management (WP-05). To reduce this risk, we reserve part of Sprint 4 (Weeks 11–12) as a contingency / Change Event buffer and track actual weekly hours worked so we can recalibrate velocity at M3.

## 3.2 Estimates

| ID | Work Item | Size / Effort Estimate | Estimation Method | Assumptions | Owner |
| --- | --- | --- | --- | --- | --- |
| WP-01 | Core Architecture, Repo, CI and 152-Exercise Dataset Setup | 6 SP (~14 h) | Planning Poker / Spike Data | A-01, A-03: The cleaned 152-exercise JSON file and Firebase configuration from the Week 3 spike can be integrated directly. | Çağatay Oruk |
| WP-02 | User Authentication and Session Management (Email/Password) | 6 SP (~14 h) | Planning Poker | A-01: The standard Firebase Auth SDK handles session refresh and error states without a custom backend server. | Çağatay Oruk |
| WP-03 | Exercise Library UI, Muscle Filtering, Search and Attribution | 8 SP (~19 h) | Planning Poker | A-03: 180×180 GIFs render smoothly in Flutter list views using cached image components. | Doğukan Direksiz |
| WP-04 | Custom Routine Builder (Create, Edit, Reorder, Delete) | 10 SP (~24 h) | Planning Poker | A-01: The Firestore document structure supports nested exercise arrays per routine within free-tier read/write limits. | Doğukan Direksiz |
| WP-05 | Active Workout Logger, Ghost Values Engine and Summary | 16 SP (~38 h) | Planning Poker + Bottom-Up | A-01: The local Firestore cache allows querying the last session's sets/reps per exercise in under 200 ms at workout start. | Çağatay Oruk |
| WP-06 | Chronological Workout History and Per-Exercise Progress | 10 SP (~24 h) | Planning Poker | A-01, A-05: Clean tables and trend summaries meet users' progress-tracking needs without heavy charting libraries. | Berat Kaan Akcan |
| WP-07 | 30-Day Plateau Analyzer (Rule Engine + Gemini Proxy + Whitelist Validator) | 14 SP (~34 h) | Planning Poker + Bottom-Up | A-02: The Gemini free tier remains available; a strict JSON prompt + a ~150-ID whitelist fully blocks hallucinations. | Çağatay Oruk & Berat Kaan Akcan |
| WP-08 | UX Enhancements (Calendar View, Google Sign-In, 3 Starter Programs) | 6 SP (~14 h) | Planning Poker | A-04: The team sustains its planned velocity in Sprints 1–2; this is the first package to be cut if the schedule slips or the Change Event is large. | Doğukan Direksiz |
| PM-QA | Project Management, Automated/Manual Testing and Milestone Deliverables (M2–M5) | 4 SP in total (~10 h; 1 SP per sprint across 4 sprints) | Analogy (M0/M1 actuals) | A-04: Weekly board updates and test runs take a combined ~1.25 hours per week between the PM and QA leads (~10 hours over 8 weeks). | Mehmet Egemen Karagöz & Berat Kaan Akcan |

## 3.3 Assumptions Log

| ID | Assumption | Impact If Invalid | Validation Action | Owner |
| --- | --- | --- | --- | --- |
| A-01 | Flutter + Firebase Firestore (with offline persistence enabled) can query previous-session ghost values in under 200 ms and store logs without needing a custom backend database. | High: Slow data entry during an active workout, or data loss when the internet drops at the gym. | Validated by the Week 3 spike; a stress test with 60 simulated workout sessions will be run in Sprint 2 (Week 7). | Çağatay Oruk |
| A-02 | The Google Gemini API free tier (via a Firebase Cloud Functions proxy running on the Blaze plan's monthly free quota with a $0 budget alert) provides enough quota and a total response time of < 5 s for on-demand 30-day plateau explanations. | Medium: API timeouts or rate-limit errors during testing or the final presentation demo. | In Sprint 3, a 4-second API timeout (keeping the total response under 5 s), response caching per 30-day window, and a deterministic rule-based text fallback will be implemented. | Çağatay Oruk |
| A-03 | The verified static subset of ~150 exercises (with 180×180 media and the "© Gym visual" attribution) covers core user routines and satisfies the license terms. | Medium: Users cannot log a movement that is not among the ~150 items, or the media license terms are violated. | Media is bundled strictly for non-commercial academic course evaluation at unmodified 180×180 resolution; UI and README attributions were audited and verified in Sprint 1; custom text-based exercises are allowed for logging while AI suggestions remain limited to the 152 verified items. | Doğukan Direksiz |
| A-04 | Each of the 4 team members can consistently commit 6–8 hours per week (~20 SP per 2-week sprint); a 20% drop is expected during the midterm exam period in Weeks 7–9. | High: A slip in Sprint 2 could put the M3 Midterm Review deliverable at risk. | Pull WP-01 – WP-04 into Sprint 1; track the weekly burndown chart every Sunday and apply the MoSCoW cut order if velocity falls below 16 SP. | Mehmet Egemen Karagöz |
| A-05 | The deterministic rule (neither max weight nor total volume increasing for the same exercise over ≥3 sessions in the last 30 days) correctly captures amateur plateaus. | Medium: False positives/negatives in plateau detection reduce the feature's usefulness. | In Sprint 3, validate the rule logic with unit tests against 10 synthetic 30-day workout datasets (progressing, stalled, deload, irregular). | Berat Kaan Akcan |

# 4. Schedule / Release Plan

| Milestone / Sprint | Goal | Start | End | Key Dependencies | Exit Criteria |
| --- | --- | --- | --- | --- | --- |
| M0 & M1 (Weeks 1–4) [Completed] | Project Selection, Technical Spike and Project Charter | 21.09.2026 | 22.10.2026 | Team setup, dataset selection, Week 3 Flutter/Firebase spike | M0 and M1 reports submitted; repo, board and 152-exercise dataset prepared. |
| M2 & Sprint 1 (Weeks 5–6) | Baseline Approval, Authentication, Exercise Library and Routine Builder (WP-01, WP-02, WP-03, WP-04) | 23.10.2026 | 08.11.2026 | Firebase project setup; cleaned 152-exercise JSON asset bundle | M2 submitted (01.11.2026); users can sign up, filter the ~150 exercises with "© Gym visual" attribution, and create and edit custom routines. |
| Sprint 2 & M3 Midterm Review (Weeks 7–8) | Active Workout Logger with Ghost Values and Workout History (WP-05, WP-06) — Core MVP Completion | 09.11.2026 | 22.11.2026 | Completion of WP-03 (Exercise Library) and WP-04 (Routine Builder) | 100% of Must features pass the DoD; ghost values load in under 200 ms; the M3 Midterm Report and live MVP deliverable are submitted. |
| Sprint 3 (Weeks 9–10) | On-Demand 30-Day Plateau Analyzer and Gemini AI Proxy (WP-07) + Course Change Event Analysis | 23.11.2026 | 06.12.2026 | WP-05 & WP-06 history data; Gemini API backend proxy | The rule-based plateau detector + whitelist-validated Gemini explanation work with a fallback; a formal Change Request (CR) and Impact Analysis are recorded. |
| Sprint 4 & M4 Control Report (Weeks 11–12) | Secondary UX Features (WP-08: Calendar, Starter Programs, Google Sign-In), Change Adaptation and QA Hardening | 07.12.2026 | 20.12.2026 | All Must features finished and the Change Event decision approved | The M4 Project Control and Adaptation Report is submitted; the full regression test suite passes with zero critical defects. |
| M5 Closure & Final Presentation (Weeks 13–14) | Final Product Polish, Demo Video/Presentation, Retrospective and Project Closure | 21.12.2026 | 03.01.2027 | Completion of Sprint 1–4 deliverables and QA sign-off | M5 Final Report, peer evaluations, lessons learned and the Week 14 Live Final Presentation completed. |

# 5. Organization and Communication

## 5.1 RACI Matrix

| Activity | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) |
| --- | --- | --- | --- | --- |
| Project Planning, Schedule Tracking and Weekly Status Reports | Mehmet Egemen Karagöz (PM) | Mehmet Egemen Karagöz (PM) | Doğukan Direksiz, Çağatay Oruk, Berat Kaan Akcan | Course Instructor & Whole Team |
| Backlog Prioritization (MoSCoW), Scope Control and UX Requirements | Doğukan Direksiz (PO) | Doğukan Direksiz (PO) | Mehmet Egemen Karagöz, Çağatay Oruk | Berat Kaan Akcan |
| Architecture, Database/Firebase Integration and AI Proxy Development | Çağatay Oruk (Tech Lead) | Çağatay Oruk (Tech Lead) | Doğukan Direksiz, Berat Kaan Akcan | Mehmet Egemen Karagöz |
| Mobile UI Feature Development (Library, Routines, Logger, History) | Çağatay Oruk, Doğukan Direksiz, Berat Kaan Akcan | Çağatay Oruk (Tech Lead) | Mehmet Egemen Karagöz | Whole Team |
| Quality Assurance, Unit/Integration Testing and DoD Verification | Berat Kaan Akcan (QA Lead) | Berat Kaan Akcan (QA Lead) | Çağatay Oruk, Doğukan Direksiz | Mehmet Egemen Karagöz |
| Milestone Deliverables (M0–M5), Metrics and Risk Register Maintenance | Mehmet Egemen Karagöz (PM), Berat Kaan Akcan (QA) | Mehmet Egemen Karagöz (PM) | Doğukan Direksiz, Çağatay Oruk | Course Instructor |

## 5.2 Communication Plan

| Event / Channel | Purpose | Participants | Frequency | Output |
| --- | --- | --- | --- | --- |
| Sprint Planning and Kick-off Meeting (Discord Voice / In Person) | Select sprint backlog items, confirm Story Point capacity and assign task owners on GitHub Projects. | All 4 Team Members | Biweekly (every other Monday, 45 min) | Locked Sprint Backlog and sprint goal note on GitHub Projects |
| Mid-Week Technical and Blocker Sync (Discord / WhatsApp) | Check progress on active tasks, resolve technical/Firebase blockers and flag new risks early. | All 4 Team Members | Weekly (every Thursday, 20 min) + asynchronous daily updates | Updated task cards on the board and blocker resolution actions |
| Weekly Review and Status Report Preparation (Discord + Shared Document) | Review completed PRs against the Definition of Done (DoD), compare Planned vs. Actual and compile the Weekly Report. | All 4 Team Members (led by the PM) | Weekly (every Sunday evening, 30 min) | Weekly Status Report submitted to DYS and updated metrics |
| GitHub Pull Requests and Project Board | Asynchronous code review, acceptance criteria verification and traceable evidence links. | Developer + Tech Lead / QA Lead reviewer | Continuous (for every feature/fix branch) | Reviewed and merged PRs with test verification comments |
| DYS Submissions and Escalation to the Course Instructor | Submit the formal Milestone Reports (M0–M5) and weekly reports; report critical deadline risks > 48 hours in advance. | Project Manager -> Course Instructor (Asst. Prof. Erkut Tekeli) | Per milestone & weekly (immediate notice if needed) | Graded milestone deliverables and formal change/risk records |

# 6. Initial Risk Register

| ID | Risk | Probability | Impact | Priority | Mitigation / Response Plan | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-03 | Scope Creep and Exam-Period Schedule Squeeze: The midterm exam period (Weeks 7–9) or unnecessary feature additions delay the core Must workout logger features. | High | High | 1 - Critical (High×High) | Freeze the Must scope at M2; pull WP-01–WP-04 into Sprint 1; if velocity falls below 16 SP/sprint, apply the strict MoSCoW cut order (cut Starter Programs, Calendar View and Google Sign-In first). | Mehmet Egemen Karagöz (PM) | Open (Actively Monitored) |
| R-02 | AI Hallucination or Unsafe Exercise Suggestions: The Gemini model suggests non-existent exercises or gives medical advice. | Medium | High | 2 - High (Medium×High) | Compute plateaus deterministically with local math rules first; send valid library IDs in the prompt; filter the AI JSON response against the ~150-exercise whitelist (discard non-matches); show the "Advisory only — not medical advice" notice. | Çağatay Oruk (Tech Lead) | Open |
| R-04 | User Privacy Leak to an External LLM: Sending workout logs to the free-tier Gemini API exposes personal identifiers. | Medium | High | 3 - High (Medium×High) | Strip all personal data (name, email, UID) before calling the backend proxy; send only anonymous exercise IDs and aggregated weight/rep counts; show a user notice before analysis. | Berat Kaan Akcan (QA Lead) | Open |
| R-01 | Dataset Media License Non-Compliance: Media from "hasaneyldrm/exercises-dataset" requires the 180×180 resolution limit and the mandatory "© Gym visual" attribution. | Medium | Medium | 4 - Medium (Medium×Medium) | Bundle the original 180×180 media files unmodified strictly for non-commercial academic course evaluation; display the mandatory "© Gym visual" attribution on the Exercise Library screen, the exercise detail view and the GitHub README. | Doğukan Direksiz (PO) | Open (Resolved in Design) |
| R-05 | Gemini API Quota Exhaustion, Deprecation or Timeout: Free-tier rate limits or network errors block the 30-day analysis screen. | Medium | Medium | 5 - Medium (Medium×Medium) | Keep the model name in a single configuration constant; set a 4-second timeout (keeping total user wait time under 5 s); if the API fails, automatically show a pre-formatted deterministic rule-based plateau summary and static alternative exercises. | Çağatay Oruk (Tech Lead) | Open |
| R-06 | Active Logger State Loss or Slow Ghost-Value Queries: The app crashes during fast set entry, or a slow Firestore query blocks the user. | Low | Medium | 6 - Low (Low×Medium) | Enable Firestore local persistence and cache the active workout state locally on every set entry; < 50 ms query performance was verified in the Week 3 spike. | Çağatay Oruk (Tech Lead) | Mitigated (Monitored) |

# 7. Baseline Approval

Approved Baseline Definition:

• Version 1.0 of this M2 Report constitutes the official GymGym-A Project Plan Baseline, unanimously approved by all four team members on 01.11.2026. It locks the Scope Baseline (WP-01 – WP-08 and out-of-scope boundaries), the Effort Baseline (80 Story Points / 192 ideal hours) and the 4-Sprint Release Schedule targeting 100% Must completion by M3 (Weeks 8–9).

Change-Control Rule and Governance Process:

1. Change Logging: Any proposed change to the Must scope, database schema, external dependencies or sprint deadlines (including the course Change Event in Weeks 9–12) must be opened as a formal Change Request (CR) card on GitHub Projects.

2. Impact Analysis: Before any development starts, the Product Owner (PO) and Technical Lead must document the change's impact across five dimensions: Scope, Schedule, Effort (Story Points), Quality/Testing and Risk.

3. Approval Thresholds:

- Minor adjustments (< 2 Story Points, not affecting Must acceptance criteria or milestone dates) can be jointly approved by the Product Owner and Technical Lead in the weekly meeting.

- Major changes (≥ 2 Story Points, adding/removing any Must or Should work package, or shifting milestone deadlines) require a unanimous review by the whole team and a corresponding scope trade-off according to our MoSCoW cut order so that total remaining effort does not exceed team capacity.

4. Traceability: All approved changes update the baseline version (e.g. v1.1) and are recorded in the M3/M4 reports together with the related GitHub PR and board card links.

# 8. Planned vs. Actual

| Planned Activity | Actual Result | Variance | Cause | Corrective Action |
| --- | --- | --- | --- | --- |
| M1 Project Initiation Report Submission (by 22.10.2026) | Submitted on 22.10.2026 with a complete Project Charter, Stakeholder Map and Hybrid delivery rationale. | 0 days (On time) | Clear task allocation across the 4 team roles. | No corrective action needed. |
| Breakdown of the M1 Scope into Epics, Work Packages and Acceptance Criteria (by 25.10.2026) | 8 MoSCoW-labeled Epics (WP-01 – WP-08) and 16 user stories created on GitHub Projects. | 0 days (On time) | Built directly on the M0/M1 scope tables and the Week 3 competitor analysis. | No corrective action needed. |
| Planning Poker Estimation and Completion of the M2 Baseline Report (by 01.11.2026) | Estimation (80 SP / 192 h), Assumptions Log, 4-Sprint Schedule, RACI and Risk Priority matrix completed. | 0 days (On time) | Team consensus reached in the Planning Poker session on 27.10.2026. | Track actual hours spent per work package from Sprint 1 onward to measure estimation accuracy at M3. |
| Sprint 1 Environment Kick-off (Flutter skeleton + 152-exercise JSON import) | Project skeleton set up and the 152-exercise JSON asset added to the repository; the Firebase Auth screen is in development. | None (on track for the 08.11.2026 Sprint 1 exit) | Week 3 spike scripts were reused. | Continue Sprint 1 execution and monitor progress in the weekly reports. |

# 9. Next Milestone Plan (M3)

| Work Item | Owner | Target Date | Expected Evidence |
| --- | --- | --- | --- |
| Complete Sprint 1 Deliverables: Authentication (WP-02), ~150-Exercise Library with "© Gym visual" attribution (WP-03) and Routine Builder CRUD (WP-04) | Çağatay Oruk & Doğukan Direksiz | 08.11.2026 | Merged PRs, unit/widget test results and a Sprint 1 board screenshot showing WP-01–WP-04 in the Done column |
| Complete Sprint 2 Deliverables: Active Workout Logger with Ghost Values (WP-05) and Workout History (WP-06) | Çağatay Oruk & Berat Kaan Akcan | 20.11.2026 | Working MVP demonstrating ghost-value pre-fill in under 200 ms and saved workout history |
| Perform M3 Quality Verification and Velocity / Planned-vs-Actual Metric Analysis | Berat Kaan Akcan (QA) & Mehmet Egemen Karagöz (PM) | 21.11.2026 | Test run log against acceptance criteria, Sprint 1–2 burndown chart and effort variance table |
| Compile and Submit the M3 Midterm Project Review Report and Live Product Evidence | Whole Team (Coordination: Mehmet Egemen Karagöz) | 22.11.2026 (End of Week 8) | M3 Report submitted to DYS, demo recording/screenshots and an updated GitHub Project Board |

# 10. Individual Contributions

| Team Member | Contribution Description | Evidence |
| --- | --- | --- |
| Mehmet Egemen Karagöz (230717063 – PM) | Wrote the Executive Summary, Schedule/Release Plan (Section 4), RACI and Communication Plan (Section 5), Baseline Approval (Section 7) and Planned vs. Actual sections; facilitated the Planning Poker session. | M2 Report Sections 1, 4, 5, 7, 8, 9; GitHub Projects sprint milestone setup. |
| Doğukan Direksiz (230717015 – PO) | Defined the 8 Work Packages and Acceptance Criteria in the Scope Baseline (Section 2.1), wrote the Scope Boundaries and MoSCoW cut order (Section 2.2), and created the GitHub backlog cards. | M2 Report Sections 2.1, 2.2; GitHub task cards and acceptance criteria labels. |
| Çağatay Oruk (230717041 – Tech Lead) | Led the bottom-up technical task breakdown and Story Point estimation (Sections 3.1, 3.2), validated the technical assumptions (A-01–A-03) and set up the Sprint 1 Flutter + dataset codebase. | M2 Report Sections 3.1, 3.2, 3.3; Sprint 1 repository commits and the dataset bundle. |
| Berat Kaan Akcan (230717052 – QA Lead) | Created the testable Acceptance Criteria and the Definition of Done (DoD), updated the Risk Register with Probability×Impact priority ranking (Section 6) and validated the plateau-rule assumption (A-05). | M2 Report Sections 3.3 (A-05), 6, 10 and Appendix item 3 (DoD); QA test checklist in the repository docs. |

# Appendix: Evidence

1. GitHub Repository (Code, Documents and Dataset): https://github.com/GymGym-A-Project/GymGym-A-SE3003

2. GitHub Project Board (Backlog, Sprint Columns and WBS Cards): https://github.com/users/se-230717041/projects/1/views/1?layout_template=board

3. Definition of Done (DoD) Applied to All Work Packages:

(a) Code compiles without warnings and follows the Flutter/Dart lint rules;

(b) The feature passes all specified Work Package Acceptance Criteria on an Android/iOS emulator;

(c) The Pull Request is reviewed and approved by at least one teammate (Tech Lead or QA Lead);

(d) Unit/validation tests pass (mandatory for plateau detection rules and the AI whitelist filter);

(e) Mandatory attributions ("© Gym visual" and the AI advisory notice) are kept on the relevant screens;

(f) The related GitHub Project Board card is moved to the Done column with the PR evidence link.

4. Estimation and Capacity Summary: 8 Work Packages + PM/QA = 80 Story Points (192 ideal hours), distributed across 4 two-week sprints (an average of 20 SP/sprint; Must packages are front-loaded into Sprints 1–2).